## Implementation Plan Blank
Metrics-Based Process Mapping Future State Implementation Plan
Process |  |  |  |  | Plan Review Dates
Process Owner
Improvement Leadership Sponsor
Mapping Facilitator
Date Created
Mapping Step # | Problem to be Solved or Proposed Countermeasure | Notes | Exec. Method * | Owner | Planned Timeline for Execution | [11 empty] | Status
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
0% | bar: Planned Timeline for Execution 1
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Agreement
Executive Sponsor |  |  |  |  | Planned Timeline for Execution 1: Value Stream Mapping Facilitator
Signature: |  |  |  |  | Planned Timeline for Execution 1: Signature:
Date: |  |  |  |  | Planned Timeline for Execution 1: Date:
* Execution Method = JDI (Just-do-it), KE (Kaizen Event), or Proj (Project) |  |  |  |  | Planned Timeline for Execution 1: v5 Dec 2014; Planned Timeline for Execution 7: © 2014 The Karen Martin Group, Inc.

## Implementation Plan Example
Metrics-Based Process Mapping Future State Implementation Plan
Process |  | Outpatient Imaging |  |  |  | Plan Review Dates
Process Owner |  | Allen Ward |  |  |  | 2014-11-01
Improvement Leadership Sponsor |  | Paul Scanner |  |  |  | 2014-11-21
Mapping Facilitator |  | Dave Parks |  |  |  | 2014-12-13
Date Created |  | 2014-10-18 |  |  |  | 2015-01-10
Mapping Step # | Problem to be Solved or Proposed Countermeasure | Notes |  | Exec. Method* | Owner | Planned Timeline for Execution | [11 empty] | Status
[6 empty] | O | O | O | O | N | N | N | N | D | D | D | D
1 | Improve quality of referral to 85% | Implement standard work for referral process |  | KE | Sean Michaels | [12 empty] | 100%
2 | Reduce lead time between scheduling and preregistration step to 45 minutes | Cross-train and co-locate work teams |  | PROJ | Dianne Marie | [12 empty] | 75%
3 | Only one check in per patient | Collect copays in Imaging |  | KE | Ryan Austin | [12 empty] | 50%
3 | Reduce wait time in waiting area by 50% | Balance work / level demand |  | KE | Dianne Marie | [12 empty] | 50%
5 | Eliminate 6 hour lead time associated with transcription step | Implement voice recognition technology |  | PROJ | Dave Gerald | [12 empty] | 50%
6 | Eliminate redundant data entry | Auto populate between PACS and Meditech |  | PROJ | Dave Gerald | [12 empty] | 25%
4 | Visually managed inventory; no outages or expired items | 5S CT supplies area; implement kanban |  | KE | Michael O'Shea | [12 empty] | 100%
6 | Reduce report release turnaround to one hour | Assign value-stream specific radiologists |  | PROJ | Martha Allen | [12 empty] | 25%
7 | Reduce report delivery LT to 30 minutes | Increase % of physicians receiving electronic delivery |  | PROJ | Martha Allen | [12 empty] | 0%
6 | Reduce LT at image review to 1 day | Visual metrics and indicators |  | JDI | Dave Gerald | [12 empty] | 100%
Agreement
Executive Sponsor |  |  | Value Stream Champion |  |  | Value Stream Mapping Facilitator
Signature: |  |  | Signature: |  |  | Signature:
Date: |  |  | Date: |  |  | Date:
* Execution Method = JDI (Just-do-it), KE (Kaizen Event), or Proj (Project) | [5 empty] | v5 Dec 2014 | [6 empty] | © 2014 The Karen Martin Group, Inc.

## More Info
Order Now!
Karen Martin, President The Karen Martin Group, Inc. 858.677.6799
www.ksmartin.com